## Slide 1: Home Affairs Programme in Bulgaria: From Development to Actual Implementation Cooperation Committee Meeting 28 November 2018

## Slide 2: Agenda
13:00 – 14:00 State of play under the Home Affairs Programme
14:00 – 14:30 Main aspects of the Management and Control Systems of the Home Affairs Programme
14:30 – 15:00 Proposals for donor project partnerships under PDP 2 and PDP 3. Pre-eligibility conditions in the Programme agreement
15:00 – 15:30 Summary of proposals for bilateral initiatives submitted by promoters and discussion on use of the funds for bilateral relations and approval of priority actions to be supported under the fund
15:30 – 16:00 A.O.B.
Third Cooperation Committee Meeting

## Slide 3: State of play
Last CC meeting was on 24 April 2018
Programme Agreement was signed on 23 May 2018 in Sofia
Programme Implementation Agreement was concluded on 10 July 2018
Two BG-NO expert meetings were carried out under PDP3 and PDP7 in Sofia and a joint PDP1 & 2 meeting in Oslo
Details of programme partnership agreements are being discussed among partners
Meetings between the NFP and POs were held for discussion of cross-cutting issues concerning all programmes in Bulgaria
Description of the MCS of the Home Affairs Programme were submitted to the NFP and the Certifying Authority on 18.10.2018
Next steps:
  Official Launch of the programme will be on 29.11.2018
  Development of draft partnership agreements: before the signing of the project contract (Art. 7.7 of the Regulation)
  Submission and appraisal of PDPs: Q1 of 2019
  Conclusion of project contracts: Q2 of 2019
  a legal entity independent of and unrelated to the Programme Operator will be selected to appraise the pre-defined projects (p. 5 of the General Conditions in Annex I to the PA)
  Prior to the first disbursement to the pre-defined projects, NMFA shall approve the entity, independent of the PO, to be charged with verification of payment claims and project outputs of PDPs of MoI project promoters (p. 6 of the General Conditions in Annex I to the PA)

## Slide 4: Management and Control Systems
Structure of the document:
General information
Legal and institutional framework
Organisation and functions of the PO
Development of the programme
Selection of projects
Procedure for the selection of external independent evaluators
Procedures before conclusion of contracts
Conflict of interest
Conclusion of project contracts
Amendment of project contracts
Termination of project contracts
Project partnerships and agreements
Control of public procurement of project promoters
Monitoring of programme implementation
Verification of payment claims
Rules for payments
Arrangement of the accounting process in the PO
Eligibility of expenditures of the programme
Financial management
Forecast of likely payments
Suspension of payments
Accounting
Irregularities
Financial corrections
Information and publicity
Audit trail
Procedures for amendment of the MCS

## Slide 5: Donor project partnerships under PDP2 and PDP3.
Donor project partnerships proposals in email from POD of 16.10.2018:
  Regarding PDP 2 'Increasing the administrative capacity of the national authorities in the asylum and migration area': inclusion of National Police Immigration Service (NPIS) in mutually beneficial activities as a donor project partner under PDP 2 will strengthen the already fruitful migration and police cooperation between Bulgaria and Norway. If NPIS is included as partner, it is expected that all costs related to their participation in PDP 2 will be covered within the total grant amount of €1 506 000 as outlined the in the programme agreement.
  Regarding PDP 3 'Increasing the capacity of General Directorate "Combating Organized Crime" for more effective investigation of organized and transnational crime‘: The discussions between General Directorate "Combating Organized Crime" and Kripos are on-going. During these discussions it has become increasingly clear that Oslo Police District will be heavily involved in many of the foreseen activities in PDP 3. For purely practical purposes, it is requested that Oslo Police District will be made donor project partner alongside Kripos in PDP3.
Possible amendment of the Programme Ageement?

## Slide 6: Pre-eligibility conditions
Pre-eligibility conditions in accordance with Annex I to the PA:
No costs shall be eligible under pre-defined projects no. 1, 9 and 14 (numbering under Section 5.1 of Annex II to the Programme Agreement) before the revised detailed descriptions and budgets for the pre-defined projects have been submitted and approved by the NMFA.
PDP 1 – developed partnership agreement regulating obligations of the partners in acc. with recommendations of the external evaluation of the project.
PDP 9 – partnership between AMoI and OSCE.
PDP 14 – revised detailed description and budget provided to PO. Next steps?

## Slide 7: Home Affairs Programme – financial figures
Total budget – 25 294 118 euro
  NFM Grant – 21 500 000 euro
  National co-financing – 3 794 118 euro
  Amount received (advance payment) – 4 464 992 euro
  NFM Grant – 3 794 118 euro
  National co-financing – 670 874 euro
  Spent amount – 14 830 euro
  Bilateral fund – 100 000 euro
  Amount received (advance payment) – 50 000 euro
  Spent amount – 33 280 euro

## Slide 8: Thank you!
https://www.eeagrants.bg/ https://www.mvr.bg/dmp
Mail: dmp@mvr.bg