## Risk matrix
Programme Name: | Home Affairs (Bulgaria)
Programmatic risks
Risk description | Risk related to | Likelihood | Consequence | Risk score | Response to risk | Description of response
Incorrect allocation of responsibilities at all levels of management and control | Both objectives | 1 | 2 | 1.4142 | Mitigate | Implementation of recommendations from audit/ external evaluators/ NFP/ FMO
Lack of communication between the responsible units | Both objectives | 1 | 2 | 1.4142 | Mitigate | Regular meetings with beneficiaries, donor programme/project partners, NFP, FMO, IPO
Lack of appropriate strategies for usage of bilateral funds | Strentgthening bilateral relations | 1 | 3 | 1.7321 | Mitigate | Implementation of recommendations from audit/ external evaluators; regular meetings with beneficiaries, donor programme/project partners, NFP, FMO, IPO
Delay in the implementation of the Programme may represent a risk for the successful achievement of its objectives | Both objectives | 2 | 3 | 2.4495 | Mitigate | Elaboration of milestones/ procurement plans; impementation of recommendations; regular meetings with beneficiaries, donor programme/project partners, NFP, FMO, IPO
Lack of controls within the project promoters' institutions | Reducing social and economic disparities | 2 | 2 | 2 | Mitigate | Guidelines provided by FMO/PO/NFP, regular meetings between PO and PPs
Operational risks
Risk description | Risk related to | Likelihood | Consequence | Risk score | Response to risk | Description of response
Shortage of qualified and sufficient in number staff at all levels of the System for Management and Control |  | 2 | 2 | 2 | Mitigate | Assessment of staff needs, hiring of additional staff, training for staff of the Programme Operator and the Project Promoters
Non-execution/wrongful execution of the internal procedures for monitoring and control |  | 1 | 2 | 1.4142 | Accept | Elaboration of monitoring plans to manage the risk level; implementation of mitigation measures, if necessary
Inability to guarantee the quality of the documentation of open calls or tender procedures |  | 2 | 2 | 2 | Mitigate | Enhancing the qualification of PO/PPs experts; providing time to re-publish the call/tender procedure; development of a feasible schedules for the start of the calls/tender procedures
Inability to obtain reliable information from project promoters for the purposes of financial reporting leading to repetitive re-submission and time wasting |  | 2 | 2 | 2 | Mitigate | Enhancing the qualification of PO/PPs experts; distribution of guidelines/Rules of Procedure on the organisation and the implementation of the planned actions; monthly meetings of PO and PPs
System for recording / reporting / following-up / recovering irregularities is not properly designed and/or does not efficiently work |  | 2 | 1 | 1.4142 | Accept | Setting up procedures in line with national/ European law which allow monitoring and responding if risk level increases; assessment of the training needs in this area for project promoters/ PO staff
OVERALL RISK OF THE PROGRAMME |  | Likelihood | Consequence | Risk score
|  | 2 | 2 | 2
Colour coding of risk levels
Low
Medium-low
Medium-high
High

## Description of risk categories
Programmatic risks
Risks related to inadequate programme/project strategy or processes, technological issues, obtaining permits, and/or lack of time for proper implementation. Risks related to improper strategies put in place to reach the bilateral objective, including using bilateral funds, and actively involving Donor State entities (DPPS and dpps).
Operational risks
Risks related to the systems to monitor, measure and communicate results. Includes risk related to the POs’ ability to attract, develop and/or retain the right staff in adequate numbers. Risks related to the deviations from key fiduciary principles of: economy, efficiency, effectiveness, integrity, openness and transparency, and fairness and accountability. Includes risks related to improper or poorly defined procedures or excessively burdensome controls leading to delays, through insufficient financial controls leading to irregularities not being addressed, financial corrections being imposed. Also includes risks related to favouritism, including in selection processes (open calls and public procurements).
Back to risk matrix

## Explanation of risk scoring
Criteria | 1 | 2 | 3 | 4
Likelihood of occurrence | Very unlikely | Unlikely | Likely | Almost certain
Consequence for programme outcomes | Minimal | Moderate | Serious | Very serious
Back to risk matrix

## Sheet4 (hidden)
Likelihood | Consequence
1 | 1
2 | 2
3 | 3
4 | 4

## Sheet5 (hidden)
Avoid/terminate
Transfer/share
Accept
Mitigate

## Sheet6 (hidden)
Reducing social and economic disparities
Strentgthening bilateral relations
Both objectives

## Sheet1 (hidden)
1 Low
2 Medium low
3 Medium high
4 High