## Slide 1: Home Affairs Programme in Bulgaria Cooperation Committee Meeting 13 May 2019

## Slide 2: Agenda
13:45 – 13:50 Opening of the meeting
13:50 – 14:15 State of play: Information on the updated milestone and risk management plans of the Home Affairs Programme
14:15 – 14:45 Discussion
14:45 – 15:00 Presentation of suggested bilateral activities and procedures for application under the fund for bilateral relations
15:00 – 15:30 Discussion
15:30 – 16:00 AOB
4th Cooperation Committee Meeting

## Slide 3: State of play
Last CC meeting was on 28 November 2018;
Description of the MCS of the Home Affairs Programme was approved by the Audit Authority on 05 March 2019;
FMO approved the entity, independent of the PO, charged with verification of payment claims and project outputs of PDPs of MoI project promoters (p. 6 of the General Conditions in Annex I to the PA) on 18 March 2019;
Meeting with potential candidate for independent evaluator of the pre-defined projects held on 9 May 2019;
Draft invitations for the first batch of pre-defined projects (No 4, 5, 6, 7, 8) were elaborated in Bulgarian and English; the signature of project contract for these projects is planned for September 9th, 2019;
The draft partnership agreement for PDP7 between the Research Institute of Forensic Sciences and Kripos (National Criminal Investigation Service) was finalized; the agreement is expected to be signed on 25 June 2019;
The first draft of the partnership agreement with National Police Immigration Service (NPIS) and Migration Directorate under PDP2 “Increasing the administrative capacity of the national authorities in the asylum and migration area” was elaborated and the Programme Operator provided initial comments;
Pre-eligibility conditions:
  PDP 1: PP, NFP, PO, and government and municipal authorities are involved in the process of finding an appropriate site for the centre for unaccompanied minors;
  PDP 9: FMO facilitated a telephone conference between PO, AMoI and OSCE Office for Democratic Institutions and Human Rights; the partners (AMoI and ODIHR) agreed broadly on the activities which will be implemented under the project; ODIHR are still expected to submit their written contribution to be included into the project description;
  PDP 14: the revised project description and budget were consulted with the DPPs and the IPO. The project promoter decided to modify the project description on the basis of the Council of Europe’s comments. PO will send the project to FMO for approval by 17 May 2019

## Slide 4: Milestone Plan
No | Milestone | Date of achievement (CN to PA) | Expected date of achievement | No | Milestone | Date of achievement (CN to PA) | Expected date of achievement
1 | Programme Agreement signed | 01.06.2018 | 23.05.2018 | 13 | Conference on expert forensic examinations held | 31.08.2021 | 31.01.2022
2 | Programme Implementation Agreement signed | 01.07.2018 | 10.07.2018 | 14 | Trainings on the asylum and migration issues completed | 30.11.2021 | 30.04.2022
3 | Programme implementation launched | 31.10.2018 | 29.11.2018 | 15 | Anti-corruption measures and operational tactics introduced in Bulgarian Ministry of Interior | 01.02.2022 | 01.07.2022
4 | Request for modification of the Programme Agreement submitted | - | 30.06.2019 | 16 | Call for proposals completed | 01.04.2019 | 01.04.2020
5 | Project contracts signed for PDPs no. 4, 5, 6, 7, 8 | 30.11.2018 | 12.07.2019 | 17 | Project contracts signed for selected projects | 01.06.2019 | 01.06.2020
6 | Project contracts signed for pre-defined projects no. 2, 3, 9-14 | 30.11.2018 | 31.10.2019 | 18 | Annual Programme Report | 15 February each year | 15 February each year
7 | Project contract signed for PDP1 | 30.11.2018 | 31.11.2019 | 19 | IFR | 15 March, 15 September | 15 March, 15 September
8 | A detailed description of the Management and Control Systems submitted to the NFP | 01.12.2018 | 18.10.2018 | 20 | All projects completed | 30.04.2024 | 30.04.2024
9 | Permit obtained for change in the use of the building designated for Interim Care Facility for Unaccompanied Minors | 31.03.2019 | 31.03.2020 | 21 | Programme closing conference held | 31.12.2024 | 31.12.2024
10 | Establishment the Interim Care Facility completed | 30.09.2020 | 30.09.2021 | 22 | Final Programme Report | 30.04.2025 | 30.04.2025
11 | Coverage of law enforcement communication system expanded in southwest Bulgaria | 31.12.2020 | 31.05.2021 | 23 | Final balance | 30.04.2025 | 30.04.2025
12 | Automated Information System “Domestic Violence” developed and operational | 31.05.2021 | 31.10.2021 |  |  |  | 

## Slide 5: Risk Management Plan
PDP 1 – lack of site/building; several new options are discussed (Elhovo, Kremikovtsi, Marchaevo village near Sofia);
PDP 2 - delay in project implementation due to inclusion of a new partner (National Police Immigration Service) and prolonged process of agreeing on activities and budget between partners;
PDP 3 - delay in project implementation due to inclusion of a new partner (Oslo District Police) and prolonged process of agreeing on activities and budget between partners;
PDP 9 – ineffective communication between the project promoter and the potential project partner (OSCE); OSCE submitted new proposals for activities on 07.05.2019 as basis for future discussions between project partners;
PDP 14 – pre-eligibility condition is imposed: the revised detailed description and budget will be sent to FMO for approval by 17 May 2019; in addition, systematic delays in project implementation were identified with the same project promoter under other funds managed by the Programme Operator, pending cancellation of the project
Identification of new risks related to pre-defined projects:

## Slide 6: Bilateral Activities
Introduction of monitoring tool on PDP1 in order to evaluate the quality of services provided in the interim care facility;
Training and capacity building in the area of reception of vulnerable groups (including UAMs), including conferences in Bulgaria and /or Norway with experts from the two countries as well as possible participation from Greece and Romania;
2 proposals of the Commission for Combating Corruption and Illegal Assets Forfeiture:
  Exchange of experience in the anti-corruption field (legal basis, methodologies, and best practices); and
  Partnerships for successful institutional practices for prevention of corruption
Video surveillance training seminar: training with NO lecturers for exchange of best practice and knowledge regarding use of video surveillance for increasing security in public spaces: Bulgarian General Directorate “National Police” and 1-3 experts from Innlandet Police District;
2 proposals of National Police Directorate (POD):
  Strengthened cooperation between Bulgarian and Norwegian law enforcement personnel in THB and preventive police work; and
  Combating cybercrime and human trafficking by strengthening the methods for interviews of minor victims
SYNERGY-network meetings related to domestic and gender-based violence (DGBV)

## Slide 7: Thank you!
https://www.eeagrants.bg/ https://www.mvr.bg/dmp
Mail: dmp@mvr.bg